School Operational Plan 2021-2022

“I have come in order that you might have life – life in all its fullness.” John 10:10

Christ taught us that his purpose was to give life in all its fullness. Through our Christ like attitude we seek to do the same.

This is at the heart of all we do.

| KNOWLEDGE |  |
| --- | --- |
| Quality of Education (SEF 1) |  |
| Task | Success Criteria |
| Priority 1 Through our aspirational academic and social ambition ensure all learners are supported and inspired to reach their goals and shine. |  |
| * To mitigate against the impact of school closures on our disadvantaged children, particularly in reading, writing and communication and interaction in EYFS; standards in phonics and the % reaching expected standards in R, W & M. * To mitigate against the impact of school closures on the % of children achieving GDS across all subjects and the % of children achieving the EXS standard in writing. * To ensure that SEND provision for children continues to be of a high quality throughout the curriculum. * Embed the funds of knowledge within our schools community and the local area within our curriculum. * Through staff development opportunities ensure that the concept of powerful knowledge is understood and embedded in the curriculum. | * Against established baselines children make at least the expected progress. * % of children achieving GDS is back in line with standards at the last statutory assessment point (18-19 dataset). * SEND children make the expected progress against My Plan targets. * Curriculum planning to reflect the use of funds of knowledge. * Audit of individual subject improvement plans evidence the introduction and impact of powerful knowledge. |
| Behaviour and Attitudes (SEF2) |  |
| Priority 2 To maintain and further develop a culture that celebrates positive behaviour and attitudes from all. |  |
| * To work alongside our children to create mechanisms of their design that gathers their peer’s opinions about behaviours and attitudes in school. * To revisit the principles of successful learning with our children to ensure cohesive and consistent development of positive learning behaviours. * To induct a new ‘Grow Your Brain’ lead to take this initiative to a second phase. * Review the school’s behaviour policy, alongside a working group research best practice in this area, trial new approaches. * To maintain a strong and impactful focus on attendance whilst recognising circumstances beyond our control may arise. | * Pupil parliament successful gather children’s voice about behaviour and attitudes with appropriate action then taken. * Pupil conferences and learning walks to evidence an embedded understanding of successful learning. * Audit of improvement plan evidences positive impact. * Draft behaviour policy in place to be introduced in 22-23. * To improve on the last uninterrupted year’s (18-19) attendance of 94.6% (95.8% not including GRT). The expected target is 95.1% (not including GRT 96%) and the aspirational target 95.6% (not including GRT 96.5%). * Reduce PA in line with the national average and to improve on the last uninterrupted year’s figures. |
| Personal Development (SEF 3) |  |
| Priority 3 To go beyond the expected to consistently promote the extensive personal development of pupils. |  |
| * Ensure staff are in skilled to assess the emerging mental health and general well-being needs of the children. * Embed the assessment process to support the identification of the above linked to action in class, action through in school expertise (inclusion), action by external agencies (e.g. TIC+). * Preceding year group leads to work with following year group leads so they can influence practice to further enhance readiness. * Introduce an oracy lead within our English team to revisit the skill of debate and discussion to celebrate difference and individuality. • To audit the support now available to children and create a comprehensive map for practitioners to reference. | * Evidence of resources available to staff and training delivered. * Assessment protocols available and embedded. Inclusion team minutes to evidence children referred and action taken. * Staff meeting time allocated, provision for children adapted accordingly. * English improvement plan to include oracy initiatives. Learning walks to evidence impact. * Map for practitioners available and disseminated. |
| Leadership and Management (SEF 4) |  |
| Priority 4 To ensure the education provided by our school has a positive impact on the outcomes of all children so that they reach their goals and shine. |  |
| * To provide highly effective professional development for staff and provision for children in response to strategic analysis. * To further embed the roles of the senior leadership team and other members new to leading roles (including subject leaders) in school. * To make successful links with the Coney Hill/Milestone teaching alliance so we are able to grow our own teachers and develop staff at all levels. * Ensure our values are the golden threads seen and celebrated in our curriculum. * To introduce and embed a new school Vision which is valued and understood by the school community. * To induct those new to teaching through the ECT programme. | * Performance management, staff meeting and INSET programmes created and in turn adapted as needed. * R&Rs of all leaders in school embedded with impactful individual improvement plans, SOP, SEF and monitoring programmes created. * Successful programme of support for schools direct students in school. Delivery of training for the teaching alliance by staff in school. * Curriculum to reflect the current values in school as appropriate. * New Vision introduced and explored throughout the academic year. * ECT programme introduced and training delivered. |